BUILDEX ECOSYSTEM

Project Next Steps & Implementation Roadmap

Buildex • Buildex Capital • Buildex Connect

Prepared as a consolidated action document from the strategic briefing and subsequent project discussions.

# 1. Executive Summary

Buildex is transitioning from a product-centric interior and construction-supply business into an integrated platform ecosystem. The strategy connects three complementary businesses: Buildex for product supply, Buildex Capital for financing, and Buildex Connect for manufacturer-to-hardware marketplace services. The immediate objective is to build the data, payment, credit, marketplace and operational infrastructure required to make the ecosystem scalable while controlling financial and portfolio risk.

The next phase should focus on four foundations: (1) formal credit and risk policies, (2) reliable transaction and wallet data, (3) a measurable credit-scoring and loan-management engine, and (4) a verified manufacturer and hardware marketplace. A pilot should be deliberately small, controlled and measurable before larger credit limits are introduced.

# 2. Strategic Vision

Create a one-stop platform where hardware shops can source products, access financing, manage inventory and connect with manufacturers and service providers.

Capture chain-level data from manufacturer → Buildex → hardware → POS transaction → end consumer.

Use transaction data to improve credit decisions, inventory recommendations, customer engagement and manufacturer market intelligence.

Create ecosystem stickiness through useful financial and commercial services rather than relying only on product supply.

Develop Buildex Agents over time: verified hardware shops operating the Buildex technology stack without Buildex owning every physical outlet.

# 3. Ecosystem Structure

| Business | Primary Role | Strategic Asset |
| --- | --- | --- |
| Buildex | Product supply and distribution | Supply relationships, inventory and hardware network |
| Buildex Capital | Credit, financing and collections | Credit data, repayment history and financial products |
| Buildex Connect | Manufacturer marketplace | Manufacturer network, product catalogue and market intelligence |

# 4. Buildex Capital — Credit Programme

## 4.1 Credit Qualification & Scoring

Require a defined historical operating period before normal credit eligibility; the current proposal is a minimum six-month membership/usage period.

Measure active platform usage, turnover, payment behaviour, stock movement, cash-conversion cycle and transaction consistency.

Use available M-Pesa/payment data, bank statements, CRB information and verified business/identity records where legally permitted.

Profile the individual borrower as well as the business, with clear rules for personal guarantees, business obligations and accountability.

Use a total business credit limit as the primary facility, with optional product/category sub-limits where risk requires them.

Target a high level of platform transaction visibility; the current strategic threshold is that hardware shops process at least 80% of turnover through the system before qualifying for the main credit facility.

Use the first pilot to validate whether the proposed scoring variables actually predict repayment before increasing limits.

## 4.2 Proposed Credit Limits & Pilot

Pilot entry limit: approximately KSh 30,000 for controlled testing.

Longer-term limits may scale into the millions for consistently performing businesses; earlier strategic discussions referenced potential limits around KSh 3–4 million.

Do not automatically grant high limits based only on turnover. Limits should be derived from verified repayment capacity, cash cycle, platform activity, exposure concentration and loss experience.

Automatically review or reset available credit when outstanding balances are cleared, subject to risk rules.

## 4.3 Credit Tenors & Pricing

Initial proposed repayment cycles: 5, 10 and 14 days.

Evaluate commercial pricing for each tenor and document the economic rationale, effective cost and customer disclosure requirements.

Any pricing model based on deferred payment or increased product price must be reviewed by legal/compliance professionals before launch.

Define approval thresholds, overrides, exception handling and escalation procedures.

## 4.4 Repayment, Wallet & Collections

Provide eligible hardware businesses with a digital wallet/payment account integrated with the platform.

Route qualifying POS collections through the wallet to create reliable transaction history and facilitate repayment.

Evaluate automatic collection/sweeping mechanisms at agreed intervals, including the proposed five-day sweep cycle and loan due-date collection.

Define reserve/security requirements where appropriate.

Track Days Past Due (DPD), Non-Performing Loans (NPL), outstanding principal, expected collections, recoveries and write-offs.

Design a documented recovery process before issuing meaningful credit. The proposed 37-day recovery concept should be treated as a policy hypothesis to be validated by the credit professional and legal advisers.

# 5. Regulatory, Legal & Risk Workstream

Regulatory exposure should be treated as a design constraint, not something to be avoided through structuring. Before the lending pilot, Buildex should obtain professional Kenyan legal and regulatory advice on the applicable lending, payments, consumer-protection, data-protection, credit-reference and financial-services requirements.

Engage a qualified credit-policy/risk professional to draft the lending framework.

Engage Kenyan legal/compliance counsel to confirm the regulatory perimeter for the proposed lending, wallet and payment-collection model.

Document responsible lending, affordability, pricing, disclosure, complaints, collections and data-processing requirements.

Define portfolio concentration limits, maximum exposure per borrower, sector/geographic limits and approval authority.

Establish fraud controls, identity verification, KYB/KYC procedures and audit trails.

Do not launch or scale a credit product on the assumption that a particular business structure automatically removes regulatory obligations.

# 6. Payment & Wallet Integration

## 6.1 Immediate Requirements

Select the initial payment channels for the pilot, including the M-Pesa integration strategy.

Create a wallet/account ledger capable of recording collections, disbursements, repayments, fees and reversals.

Connect POS transactions to the wallet so the system can calculate turnover routed through Buildex.

Implement automated reconciliation between payment providers, wallet balances, POS transactions and loan accounts.

Create alerts for failed collections, insufficient wallet balance, unusual transaction behaviour and repayment risk.

## 6.2 Cash-Conversion Monitoring

Calculate average days from stock purchase to sale and from sale to cash collection.

Identify peak liquidity periods and recurring cash shortages.

Compare credit tenor against the actual cash cycle before increasing a borrower's limit.

Monitor stock velocity and gross-margin characteristics by product category.

# 7. Hardware Partner Qualification

| Criterion | Proposed Requirement | Output |
| --- | --- | --- |
| Membership history | Minimum 6 months of meaningful platform activity | Eligibility flag |
| Platform turnover | Target ≥80% of turnover processed through Buildex | Verified transaction ratio |
| Identity/KYB | Verified individual and business information | Verified profile |
| Credit history | CRB and internal repayment history where permitted | Risk indicators |
| Sales behaviour | Consistent sales and customer activity | Turnover profile |
| Stock behaviour | Healthy stock movement and replenishment | Inventory risk profile |
| Cash cycle | Demonstrated ability to convert stock into cash | Recommended tenor/limit |
| Repayment | No unexplained persistent arrears | Risk grade |

# 8. Buildex Connect — Manufacturer Marketplace

## 8.1 Onboarding & Verification

Collect KRA/tax information, BRS/business registration documents and other required company information.

Verify submitted business information through authoritative sources where integrations and permissions allow.

Use physical verification or other enhanced due diligence for higher-risk manufacturers.

Maintain manufacturer status, verification date, documents and review history.

## 8.2 Subscription Packages

| Package | Core Features |
| --- | --- |
| Free | Registration, basic product listing and pricing. |
| Basic | Visibility to hardware shops and product-view information. |
| Premium | Regional targeting, market insights and boosted search visibility. |
| VIP / Dedicated | Dedicated Buildex account management and active sales support to the hardware network. |

## 8.3 Regional Targeting

Allow manufacturers to target specific regions such as Kakamega or Kisumu.

Price regional visibility based on relevant hardware coverage, expected turnover and commercial demand.

Provide measurable campaign metrics: impressions, views, enquiries, orders and estimated conversion.

# 9. Data, Analytics & Consumer Insights

Build a unified transaction data model linking manufacturers, products, hardware shops, inventory, POS sales, payments and consumers.

Use customer purchase patterns to identify related and next-stage construction needs.

Enable compliant, permission-based SMS and digital marketing campaigns that direct consumers to participating hardware shops.

Develop dashboards for hardware performance, manufacturer demand, regional trends, product velocity and credit risk.

Treat customer and transaction data as a governed strategic asset with clear consent, access control, retention and privacy rules.

# 10. Technology Modules to Prioritize

| Priority | Module | Minimum Capability |
| --- | --- | --- |
| P0 | Credit Scoring Engine | Eligibility, score, risk grade, recommended limit, tenor and approval workflow. |
| P0 | Loan Tracker | Loan lifecycle, balances, due dates, DPD, NPL, repayments and recovery actions. |
| P0 | Wallet & Payments | Collections, ledger, reconciliation, sweeps/standing instructions and transaction history. |
| P0 | POS / Transaction Data | Sales, stock movement and turnover measurement. |
| P1 | Hardware Portal | Credit status, orders, wallet, repayments, statements and inventory. |
| P1 | Manufacturer Portal | Onboarding, verification, catalogue, subscriptions and analytics. |
| P1 | Admin / Risk Dashboard | Portfolio monitoring, approvals, exceptions, alerts and reporting. |
| P2 | Consumer Intelligence | Segmentation, recommendations and compliant campaign tools. |

# 11. Data Required Immediately

Current hardware shop stock flow and movement records.

Historical sales/turnover data.

M-Pesa/payment transaction records and, where appropriately authorized, bank statements.

Customer transaction patterns and product-level sales data.

Existing credit/repayment information.

Business registration and owner identity information required for onboarding and verification.

Product catalogue, supplier information, purchase prices and selling prices.

Historical defaults, arrears, recovery and write-off information if available.

# 12. Project Roadmap & Next Steps

| Phase | Timeline | Key Actions | Primary Owner |
| --- | --- | --- | --- |
| Phase 1 — Governance | Weeks 1–2 | Appoint credit-policy expert; obtain legal/compliance review; define lending policy and risk appetite. | Group / Management |
| Phase 2 — Data Foundation | Weeks 1–4 | Collect stock, POS, sales, payment and customer data; define data model and quality rules. | Data / Product Team |
| Phase 3 — Payment Foundation | Weeks 2–6 | Select payment channels; implement wallet ledger, M-Pesa integration and reconciliation design. | Technical Team |
| Phase 4 — Credit MVP | Weeks 3–8 | Build scoring engine, qualification rules, credit-limit calculation and approval workflow. | Technical / Risk |
| Phase 5 — Loan Operations | Weeks 4–8 | Build loan tracker, repayment schedules, DPD/NPL tracking and recovery workflow. | Technical / Risk |
| Phase 6 — Controlled Pilot | Weeks 8–12 | Select a small group of qualified hardware shops; issue controlled initial limits and monitor repayment. | Management / Risk |
| Phase 7 — Marketplace MVP | Weeks 4–10 | Launch manufacturer onboarding, catalogue, subscriptions and regional visibility. | Connect Team |
| Phase 8 — Review & Scale | After pilot | Measure default rate, repayment rate, utilization, ROI and operational performance; revise policies before scaling. | Management / Risk |

# 13. Immediate Action Register

| Action | Owner | Priority | Deliverable |
| --- | --- | --- | --- |
| Define lending criteria for hardware partners | The Group | P0 | Approved eligibility criteria |
| Define individual borrower criteria | The Group | P0 | Borrower qualification framework |
| Draft formal lending and recovery policies | Credit/Risk Professional | P0 | Credit policy and recovery manual |
| Confirm regulatory and legal requirements | Legal/Compliance | P0 | Written regulatory assessment |
| Pre-qualify pilot businesses and recommend limits | John | P0 | Pilot borrower list and proposed limits |
| Provide current stock-flow and movement data | Unassigned / Operations | P0 | Clean stock and movement dataset |
| Select payment channels | The Group | P0 | Payment-channel decision |
| Design wallet and collection process | Product/Technical | P0 | Wallet and collections specification |
| Integrate M-Pesa/payment data | Technical | P0 | Working transaction pipeline |
| Build credit-scoring MVP | Technical/Data | P0 | Scoring and limit engine |
| Build loan tracker | Technical | P0 | Loan lifecycle and portfolio dashboard |
| Build manufacturer portal | Connect/Technical | P1 | Marketplace MVP |
| Define manufacturer packages and pricing | Management/Commercial | P1 | Approved commercial model |
| Analyze hardware cash-management behaviour | Data/Finance | P1 | Cash-cycle analysis |

# 14. Credit Scoring MVP — Recommended Model Inputs

| Feature Group | Examples |
| --- | --- |
| Platform Activity | Membership duration, active days, order frequency, Buildex transaction share |
| Turnover | Daily/weekly/monthly sales, consistency, seasonality, growth |
| Stock | Stock velocity, days inventory, replenishment frequency, slow-moving stock |
| Cash Flow | Collections, wallet inflows, cash conversion cycle, payment concentration |
| Credit Behaviour | Previous facilities, utilization, repayment timeliness, DPD |
| External Risk | CRB information and permitted third-party risk data |
| Business Profile | Business age, location, customer segment, product mix |
| Fraud / Anomaly | Transaction reversals, unusual spikes, identity inconsistencies, suspicious behaviour |

# 15. Pilot Success Metrics

Repayment rate and on-time repayment rate.

30+ day delinquency and NPL rate.

Average Days Past Due.

Credit utilization and repeat borrowing rate.

Loss rate / write-off rate.

Gross margin after credit-related costs and losses.

Cash-conversion improvement for participating hardware shops.

Percentage of hardware turnover processed through Buildex.

POS-to-wallet reconciliation accuracy.

Manufacturer onboarding and marketplace engagement.

Customer acquisition and repeat-purchase performance.

# 16. Capital Plan

The immediate funding objective is KSh 4 million for the pilot. Capital deployment should be controlled through explicit portfolio and operational budgets.

| Use | Indicative Planning Principle |
| --- | --- |
| Pilot lending capital | Ring-fence a defined amount for initial facilities. |
| Risk reserve | Maintain a management-approved loss buffer before scaling. |
| Technology | Prioritize payment, credit, loan tracking and data infrastructure. |
| Compliance & professional services | Budget for legal, credit-policy and risk expertise. |
| Operations & recovery | Budget for onboarding, verification, collections and support. |

# 17. Key Decisions Required from Management

Approve the six-month data/usage qualification concept for the main credit programme.

Confirm whether the 80% Buildex turnover threshold is a hard requirement, a target or one component of a broader score.

Approve the pilot entry limit and the criteria for increasing limits.

Approve the proposed 5-, 10- and 14-day credit cycles for testing, subject to legal/commercial review.

Approve the wallet and payment-collection architecture.

Appoint the credit-policy/risk professional and legal/compliance adviser.

Confirm the initial KSh 4 million pilot capital plan.

Select the pilot hardware shops and define the pilot monitoring period.

Approve the first release scope for the Credit Scoring Engine, Loan Tracker and Manufacturer Portal.

# 18. Operating Principle for the Next Phase

Buildex should not attempt to launch the entire ecosystem at once. The recommended sequence is: data → payment visibility → credit policy → controlled credit pilot → measured repayment outcomes → marketplace expansion → consumer intelligence. This creates a feedback loop in which every transaction improves the quality of the next business decision while keeping financial exposure controlled.

Important: All lending, payment, data-sharing, automated collection, pricing and recovery mechanisms should be validated against applicable Kenyan law and regulatory requirements before production launch.

# 19. Decision & Action Tracker

| Decision / Action | Status | Owner | Due Date | Notes |
| --- | --- | --- | --- | --- |
| Credit policy expert appointed | Not Started | Management |  |  |
| Legal/regulatory review completed | Not Started | Management / Legal |  |  |
| Pilot hardware shops selected | Not Started | John / Group |  |  |
| Stock and sales dataset received | Not Started | Operations |  |  |
| Payment channel selected | Not Started | Group |  |  |
| Wallet architecture approved | Not Started | Technical / Product |  |  |
| Credit scoring MVP defined | Not Started | Data / Risk |  |  |
| Loan tracker specification approved | Not Started | Technical / Risk |  |  |
| Manufacturer onboarding requirements approved | Not Started | Connect Team |  |  |
| KSh 4M pilot capital secured | Not Started | Management |  |  |